AGENTIC SDLC FRAMEWORK

Risk Register

─────────────────────────────────────────────

Version 1.0  |  July 2026

CONFIDENTIAL

Prepared by: Engineering & Architecture Team

# 1. Risk Summary

This register consolidates risks identified across the platform's architecture, security, delivery, and operational areas during this engagement's codebase review. Risks are drawn from direct code evidence wherever possible; inferred risks are marked accordingly.

# 2. Risk Categories

Technical / Architectural

Security

Operational

Delivery / Process

Business

# 3. Risk Register

| ID | Risk | Category | Probability | Impact | Status |
| --- | --- | --- | --- | --- | --- |
| R-01 | LLM provider rate limits throttle pipeline throughput, previously causing tool-call marker leaks | Technical | Confirmed (occurred) | Medium | Mitigated — iteration budgets corrected this engagement |
| R-02 | No structured logging/APM means production issues may go undetected | Operational | High | High | Open — target-state recommendation only |
| R-03 | Unclear whether server/ is load-bearing in production | Technical | Unknown | Medium | Open — validation pending |
| R-04 | Unclear whether CI failures block production deploys | Delivery | Unknown | High | Open — validation pending |
| R-05 | Dexie/IndexedDB and PostgreSQL dual storage risks silent sync conflicts | Technical | Medium | Medium | Open — no conflict-resolution test suite found |
| R-06 | Invite-token expiry/revocation behavior unconfirmed | Security | Unknown | Medium | Open — validation pending |
| R-07 | Review gate could previously be approved with incomplete agent output | Delivery | Confirmed (was possible) | High | Closed — fixed this engagement (ReviewGateModal.tsx) |
| R-08 | Admin reset action could accidentally destroy master reference data | Operational | Confirmed risk existed by design intent | High | Mitigated — master_* tables explicitly protected |
| R-09 | Generated UI content used emoji icons, inconsistent across platforms | Delivery/UX | Confirmed (was occurring) | Low-Medium | Mitigated — inline SVG requirement added to agent prompts this engagement |

# 4. Probability and Impact Definitions

| Level | Probability Meaning | Impact Meaning |
| --- | --- | --- |
| High | Already observed or near-certain | Production incident or major rework |
| Medium | Plausible, some supporting evidence | Noticeable degradation or delay |
| Low | Possible but no direct evidence | Minor, easily corrected |

# 5. Mitigation Detail

R-01: agent iteration budgets resized per actual STEP sequence across 27 of 30 agents; concurrency capped at 5 parallel agents with 1.5s stagger.

R-02: recommend introducing a lightweight structured logger (e.g. pino) behind existing console.log call sites as a first step, per Architecture Document Section 15.

R-07: Approve and Continue is now disabled until every agent under a review gate reaches complete status, with a tooltip naming outstanding agents.

R-08: Danger Zone reset explicitly truncates only project-scoped tables, never master_* reference tables.

# 6. Contingency

If R-02 (observability gap) results in an undetected incident, the interim contingency is manual console-log inspection on the Railway service directly, since no dashboard exists yet.

If R-05 (sync conflict) causes data loss, the interim contingency is manual reconciliation from PostgreSQL as the more durable of the two stores, since Dexie is browser-local and more easily lost.

# 7. Trigger Conditions

| Risk | Trigger Condition |
| --- | --- |
| R-02 | A user reports an error with no corresponding log evidence |
| R-03 | A request to server/ times out or 404s in production |
| R-04 | A red CI run is followed by a live production issue traced to that commit |
| R-05 | Two devices/tabs report different data for the same project |

## Required Diagrams

### Diagram 1: Risk Lifecycle Flow

How a risk moves from identification to closure.

```mermaid

flowchart LR

Identified[Risk Identified]

Assessed[Assessed]

Mitigated[Mitigation Applied]

Monitored[Monitored]

Closed[Closed]

Identified --> Assessed

Assessed --> Mitigated

Mitigated --> Monitored

Monitored --> Closed

```

R-07, R-08, and R-09 have completed this full lifecycle this engagement; R-02 through R-06 remain in the Assessed or Mitigated stage.

Confidence: High.

### Diagram 2: Risk Escalation Flow

Where a risk goes if its trigger condition fires.

```mermaid

flowchart TB

Trigger[Trigger Condition Fires]

EngLead[Engineering Lead Notified]

Assess[Reassess Probability And Impact]

Action[Mitigation Or Incident Response]

Trigger --> EngLead

EngLead --> Assess

Assess --> Action

```

This is a recommended escalation path; no automated alerting exists to fire this flow today, which is itself R-02.

Assumptions: No automated trigger-detection system exists; this flow assumes manual observation.

Confidence: Medium.

### Diagram 3: Risk Category Map

Distribution of the 9 register entries across categories.

```mermaid

flowchart TB

Technical[Technical 3 Risks]

Operational[Operational 2 Risks]

Security[Security 1 Risk]

Delivery[Delivery 2 Risks]

UX[Delivery UX 1 Risk]

Technical --> Register[Risk Register]

Operational --> Register

Security --> Register

Delivery --> Register

UX --> Register

```

Technical risks dominate the register, consistent with this being a codebase-grounded assessment rather than a business-risk survey.

Confidence: High.

# 8. Confidence Level

Overall confidence: 0.85. High on risks with direct code evidence (R-01, R-02, R-07, R-08, R-09). Lower on risks stated as open/unknown (R-03, R-04, R-06), which are genuinely unresolved rather than assessed and found low.